## Sheet1
Archivists' Toolkit to ArchivesSpace Migration Workflow
University Library System, University of Pittsburgh
TASK | RESPONSIBILITY | START DATE | STATUS
INITIAL SETUP
Create Servers Needed (Web facing hostname: findingaids.library.pitt.edu) | Brian G / CSSD
Configure web server/database server | Brian G
Determine/setup repositories (ASC, SC, CAM, others?)
Establish user accounts/permissions | Ed
Assign groups | Ed
PREPARE FOR MIGRATION
Make copy of existing AT database to be used for migration | Brian G
Setup ArchiveSpace MySQL database | Brian G
Review source db for quality of data | Ed
Select representative sample for inspection | Ed
Increase the maximum Java heap space per requirements if needed | Brian G
MIGRATION (Initial)
Follow migration steps (see AS documentation) | Brian G
Assess migration (accessions, resources, name authority, location) | Ed
Review report: what worked and didn't? | Ed
What do we do about it: hand correct vs automate? | Ed/DRL
Employ one or both methods to deal with problem issues | Ed/DRL
Examine mapping scheme | Mike
MIGRATION (Repeat as needed)
Follow migration steps again | Brian G
Assess again | Ed
Did changes stick? If not, determine how to resolve | Ed/DRL
Continue to troubleshoot problems | Ed/DRL
Seek help from Lyrasis when needed | Ed/Brian
Deal with other unknown issues | All
Keep trying until successful | All
Meanwhile keep using AT | Ed
STAFF TRAINING
Determine what resources are available | Ed
Develop our own? | Ed
Get staff familiar with AS by playing with it | Ed
POLICY DEVELOPMENT
Create policies to govern ULS usage (best practices) | Ed/ASC
Will workflow status carry forward? | Ed
Rules for data entry, publishing, review, sign-off, etc. | Ed
MIGRATION (Final)
Freeze AT usage | Ed/Brian G
Close off any new activity | Ed
Export AT data one final time to AS | Brian G
Assess data | Ed
Begin using AS | Ed
Release Web interface to world | Brian G/CSSD
COMMUNICATION
Inform History Center | Ed
Post note on ASC/SC homepages and HP website prior to final migration | Ed
Train users: YouTube? Screen snapshots? | Ed
DIGITAL OBJECTS
Determine how this is handled/displayed in AS | DRL
UPDATE/RE-DIRECT LINKS
All finding aids will have new URLs so will need to update: | Ed/DRL
Related materials tag in FA
PittCat/MARC/WorldCat
Facebook
Wikipedia
LibGuides
Other??
AFTERWARDS
Reprint paper finding aids in Reading Room? | Ed
PDF option? | Ed
What to do with DRL browse FA feature? | Mike
ULS tags carry forward? | Mike
Assess and implement AS label generator if works for us | Ed
AS interface development: can we change look, display, etc.? | Ed/DRL
How does AS work with Islandora? | DRL
Is there functionality that does not exist that we need? What do we do about it? | Ed/DRL
Dismantle DLXS Finding Aid class (hooray!) | Brian G
Decommision server | Brian G